## Product Backlog
PAYROLL PRODUCT BACKLOG (User Story)
NO. | AS A… | I WANT TO BE ABLE TO… | SO THAT… | PRIORITY | SPRINT | STATUS
1 | VISITOR | See a user friendly UI structure | I can analyze which page I can put all the company information | HIGH | 1 | Completed
2 | VISITOR | Identify if the data put on each navigation if static or dynamic | So I can design the what to show on search engine | HIGH | 1 | Completed
3 | VISITOR | See the inquiry/contact form | So I'm able to design the mailing system | MEDIUM | 2 | Completed
4 | VISITOR | search information about the company | So I can get the information I need | HIGH | 1 | Completed
5 | ADMINISTRATOR | Register account for member | So I'm able to provide account to my employee's as a member | MEDIUM | 2 | Completed
6 | MEMBER | Update my account | I can modify if there's wrong information or updated info. | MEDIUM | 2 | Completed
7 | MEMBER | add admin information | so I'm able to see all the data of the admins | MEDIUM | 3 | Completed
8 | MEMBER | Create Client | i can manage employee to payroll system | HIGH | 3 | Completed
9 | MEMBER | add employee information | so I'm able to see all the data of the employee | HIGH | 3 | Completed
10 | MEMBER | Create a payroll per client | I must track a working days, set salary per cut off and all info. | HIGH | 4 | Completed
11 | MEMBER | Track the payroll history per client | I'm able to see all the transactions | MEDIUM | 5 | Completed
12 | MEMBER | Track employee records | able to track including personal info., previous posting, salary percut off and benefits | HIGH | 5 | Completed
13 | MEMBER | reply to inquiries | I can respond to all the inquiries | MEDIUM | 3 | Completed
14 | MEMBER | Submit payroll to super admin for validation | I can make a validation from admin | MEDIUM | 4 | Completed
15 | ADMINISTRATOR | Validate all the payroll report | the payroll will be finalized or modify | HIGH | 4 | Completed
16 | ADMINISTRATOR | see a list of member, client and employees | Monitor the system information | MEDIUM | 5 | Completed
17 | MEMBER | See the admin payroll to modify | See if there is anything to modify about the payroll | HIGH | 4 | Completed
18 | MEMBER | declare the payroll if paid | declare the process if done | MEDIUM | 5 | Completed
19 | MEMBER | declare if the employee is paid | track all the employees salary | MEDIUM | 5 | Completed
20 | ADMINISTRATOR | manage the member account | activate or deactivate the members account | MEDIUM | 3 | Completed
21 | ADMINISTRATOR | post picture on gallery | This will be shown on the website content | MEDIUM | 2 | Completed
22 | ADMINISTRATOR | Track the website visitors | For Monitoring Purpose only | LOW | 6 | Completed
23 | ADMINISTRATOR | Have all the privilege of the member | Necessary for admin account | HIGH | 6 | Completed
24 | ADMINISTRATOR | See who done the work | For Monitoring Purpose only | MEDIUM | 6 | Completed
25 | VISITOR | See all the data post by administrator | see the updated info | LOW | 6 | Completed

## Release Backlog
PAYROLL RELEASE BACKLOG
ID | TASK NAME | PROGRESS IN DAYS | PRIORITY | USER | STORY | STATUS | TOTAL DAYS
1 | Task 1 | 6 | HIGH | VISITOR | 1 | Completed | 46
2 | Task 2 | 1 | HIGH | VISITOR | 2 | Completed
3 | Task 3 | 1 | HIGH | VISITOR | 4 | Completed
4 | Task 4 | 2 | MEDIUM | ADMINISTRATOR | 21 | Completed
5 | Task 5 | 1 | MEDIUM | ADMINISTRATOR | 5 | Completed
6 | Task 6 | 1 | MEDIUM | VISITOR | 3 | Completed
7 | Task 7 | 1 | MEDIUM | MEMBER | 6 | Completed
8 | Task 8 | 1 | MEDIUM | MEMBER | 13 | Completed
9 | Task 9 | 1 | MEDIUM | MEMBER | 7 | Completed
10 | Task 10 | 1 | HIGH | MEMBER | 9 | Completed
11 | Task 11 | 1 | HIGH | MEMBER | 8 | Completed
12 | Task 12 | 1 | MEDIUM | ADMINISTRATOR | 20 | Completed
13 | Task 13 | 5 | HIGH | MEMBER | 10 | Completed
14 | Task 14 | 2 | MEDIUM | MEMBER | 14 | Completed
15 | Task 15 | 2 | HIGH | MEMBER | 17 | Completed
16 | Task 16 | 1 | HIGH | ADMINISTRATOR | 15 | Completed
17 | Task 17 | 1 | MEDIUM | MEMBER | 19 | Completed
18 | Task 18 | 1 | MEDIUM | MEMBER | 18 | Completed
19 | Task 19 | 2 | MEDIUM | MEMBER | 11 | Completed
20 | Task 20 | 2 | HIGH | MEMBER | 12 | Completed
21 | Task 21 | 1 | MEDIUM | ADMINISTRATOR | 16 | Completed
22 | Task 22 | 3 | HIGH | ADMINISTRATOR | 23 | Completed
23 | Task 3 | 1 | MEDIUM | ADMINISTRATOR | 24 | Completed
24 | Task 24 | 2 | LOW | ADMINISTRATOR | 22 | Completed
25 | Task 25 | 5 | LOW | VISITOR | 25 | Completed

## Sprint Backlog
PAYROLL SPRINT BACKLOG
TASK NAME | SPRINT READY | PRIORITY | STATUS | TOTAL DAYS
SPRINT 1
PLANNING | NO | HIGH | Completed | 1
Task 1 | NO | HIGH | Completed | 6
Task 2 | NO | HIGH | Completed | 1
Task 3 | NO | HIGH | Completed | 1
Rest Day | NO | LOW | TOTAL DAYS | 10
SPRINT 2
PLANNING | NO | HIGH | Completed | 1
Task 4 | NO | MEDIUM | Completed | 2
Task 5 | NO | MEDIUM | Completed | 1
Task 6 | NO | MEDIUM | Completed | 1
Task 7 | NO | MEDIUM | Completed | 2
Rest Day | NO | LOW | TOTAL DAYS | 8
SPRINT 3
PLANNING | NO | HIGH | Completed | 1
Task 8 | NO | MEDIUM | Completed | 1
Task 9 | NO | MEDIUM | Completed | 1
Task 10 | NO | HIGH | Completed | 1
Task 11 | NO | HIGH | Completed | 1
Task 12 | NO | MEDIUM | Completed | 1
Rest Day | NO | LOW | TOTAL DAYS | 7
SPRINT 4
PLANNING | NO | HIGH | Completed | 1
Task 13 | NO | HIGH | Completed | 5
Task 14 | NO | MEDIUM | Completed | 2
Task 15 | NO | HIGH | Completed | 2
Task 16 | NO | HIGH | Completed | 1
Rest Day | NO | LOW | TOTAL DAYS | 12
SPRINT 5
PLANNING | NO | HIGH | Completed | 1
Task 17 | NO | MEDIUM | Completed | 1
Task 18 | NO | MEDIUM | Completed | 1
Task 19 | NO | MEDIUM | Completed | 2
Task 20 | NO | HIGH | Completed | 2
Task 21 | NO | MEDIUM | Completed | 1
Rest Day | NO | LOW | TOTAL DAYS | 9
SPRINT 6
PLANNING | NO | HIGH | Completed | 1
Task 22 | NO | HIGH | Completed | 3
Task 23 | NO | MEDIUM | Completed | 1
Task 24 | NO | LOW | Completed | 2
Task 25 | NO | LOW | Completed | 5
Rest Day | NO | LOW | TOTAL DAYS | 13
TOTAL DAYS |  |  |  | 59

## Sprint Burndown Chart
SPRINT BURNDOWN CHART
Estimated effort per sprint
Backlog ID | Sprint Name | Initial Estimate | 2021-05-17 | 2021-05-27 | 2021-06-04 | 2021-06-11 | 2021-06-23 | 2021-07-02 | 2021-07-15
|  | Day 0 | Day 1 | Day 10 | Day 18 | Day 25 | Day 37 | Day 46 | Day 59
1,2,4 | Sprint 1 | 10 | 7 | 3
21,5,3,6 | Sprint 2 | 7 |  | 4 | 3 | 1
13,7,9,8,20 | Sprint 3 | 7 |  |  | 1 | 4 | 2
10,14,17,15 | Sprint 4 | 12 |  |  |  | 2 | 5 | 5
19,18,11,12,16 | Sprint 5 | 9 |  |  |  |  | 5
23,24,22,25 | Sprint 6 | 13 | [5 empty] | 7 | 8
Remaining Effort |  | 58 | 51 | 44 | 40 | 33 | 21 | 9 | 1
Ideal Trend |  | 58 | 57 | 48 | 41 | 34 | 22 | 13 | 0